## Sheet1
Product Backlog sample for Social media application
be | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Existing Customer Login | Authentication | As an existing customer, I want to log in securely so that I can access my account and previous orders. | Must Have | Not Started | Users should be able to log in using email and password. | Implement secure authentication and session management. | Fast authentication with multi-device support. | 5 days | TBD
2 | AI Assistance Chatbot | Registration | As a new customer, I want to register easily so that I can start purchasing products | Must Have | Not Started | Customers should be able to register with email and phone verification. | User registration with OTP verification | Ensure seamless sign-up experience. | 6 days | TBD
3 | Farmer Registration | Registration | As a farmer, I want an easy registration process so that I can start listing my products. | Must Have | Not Started | Farmers should be able to submit their details and get verified | AI chatbot assistance for registration guidance. | User-friendly and responsive interface. | 7 days | TBD
4 | Admin Dashboard for Product Management | Admin panel | As an admin, I want a dashboard to manage product listings so that I can monitor and approve farmer submissions. | Must Have | Not Started | Admins should be able to view, approve, and remove products. | CRUD operations for product approvals and moderation. | Secure access control for admins. | 6 days | TBD
5 | AI & Admin Support for Farmers | AI Assistance & Admin Support | As a farmer, I want AI assistance and admin support so that I can resolve any registration or listing issues. | Must Have | Not Started | AI chatbot should assist farmers, and admins should handle complex queries. | AI-driven chatbot for instant help, admin support for complex cases. | AI should be available 24/7 with minimal response delay. | 7 days | TBD
6 | Product Listing by Farmers | Product Management | s a farmer, I want to list my products with images and details so that consumers can purchase them directly. | Must Have | Not Started | Farmers should be able to add, edit, and remove product listings. | CRUD operations for product management with media upload. | Scalable database to handle large product listings. | 8 days | TBD
7 | Consumer Purchase & Cart Functionality | Shopping Experience | As a consumer, I want to add products to my cart and purchase them so that I can complete transactions smoothly. | Must Have | Not Started | Users should be able to add items to a cart and proceed to checkout. | Secure payment gateway, order tracking, and notifications. | Reliable checkout experience with minimal downtime. | 7 days | TBD
8 | Admin Access to Sales Analytics | Admin Panel | As an admin, I want to view sales analytics so that I can monitor platform performance and trends. | Should Have | Not Started | Admins should see sales reports, user activity, and revenue insights. | Dashboard with graphical insights and reports | Data should be updated in real time. | 8 days | TBD
9 | Admin Management of User Accounts | Admin Panel | As an admin, I want to manage user accounts so that I can monitor and control platform access. | Should Have | Not Started | Admins should be able to activate, deactivate, and manage users. | Role-based access control for user accounts | Secure admin-only access to user controls. | 7 days | TBD
10 | Enhanced Search Functionality | Search Enhancement | As a user, I want to find content easily so that I can quickly access the information I need without wasting time searching | Should | Backlog | 1. Search results are relevant and displayed in order of relevance. 2. Filters work correctly, refining search results. 3. User testing validates improved search experience. | Improve search algorithms for relevance.- Enhance filtering options based on user feedback. | Search queries should return results within 2 seconds.User satisfaction with search functionality should increase by 20% based on feedback. | 8 days