## Sheet1
Feature | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Planning & Research | Project Proposal, System Architecture Design | Requirement Gathering | Wireframing & UI/UX Design | - | - | - | - | -
User Management | - | User Authentication (Farmers & Consumers) | Farmer Registration & Profile Setup | Administrator Management | - | - | - | -
Core Features Development | - | - | Product Listing & Management | Search & Purchase Products, Product Filtering | - | - | - | -
AI Chatbot Integration | - | - | - |  | AI FAQ & Troubleshooting | - | Chatbot Assistance for Registration & Queries | -
Logistics & Tracking | - | - | - |  | Logistics & Delivery Integration | - | Real-Time Order Tracking | -
Testing & QA | - | - | - | - | Unit Testing | Integration Testing | User Testing & Feedback | -
Deployment & Launch | - | - | - | - | - | - | Final Release | Post-Launch Support & Monitoring